## COVER SHEET
PROJECT TIMELINES
CLIENT/SOW | Campaign Completion Overview
Asset Title | Format | Complete
"The Life-Altering Power of Excel" | EBOOK | 2017-08-16
"Anatomy of an Excel Scheduling Tool" | INFOGRAPHIC | 2017-08-18
"How Excel Turned Me Into a Major Nerd" | BLOG POST | 2017-07-21
"Excel Scheduling: 5 Best Practices" | G-BOOK | 2017-08-17
Use this optional cover sheet to share an overview of completion dates with the client. To make the dates function correctly, place an equal sign in the "complete" cell, and then select the project complete date cell on the corresponding schedule sheet, and press "enter." (Holly can walk you through this if you need help!) Add notes or anything else to this page that you think will help the client use and understand the schedule!

## TOC
Project Scheduling Tool
Table of Contents
E-Book
White Paper
G-Book
Infographic
Listicle
Ceros
Interactive Infographic
iPaper
Quiz
Assessment
MVID-A
MVID-S and MVID-KT
MVID-MM
Blog Post
Fact Sheet
Q&A
Blank

## E-BOOK
PROJECT TIMELINE
E-BOOK | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Column1 | Column2 | Column3 | Column4 | Column5 | Column6
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Outline to client | 5 | 1900-01-04 | 2017-07-06 | 1900-01-04 | 2017-07-13
Outline approval due | 1 | 1900-01-04 | 2017-07-13 | 1900-01-05 | 2017-07-14
Copy D1 to client | 3 | 1900-01-05 | 2017-07-14 | 1900-01-03 | 2017-07-19
Client feedback due | 2 | 1900-01-03 | 2017-07-19 | 1900-01-05 | 2017-07-21
Copy D2 to client | 2 | 1900-01-05 | 2017-07-21 | 1900-01-02 | 2017-07-25
Copy D2 feedback due | 2 | 1900-01-02 | 2017-07-25 | 1900-01-04 | 2017-07-27
Copy D3 & POC to client | 1 | 1900-01-04 | 2017-07-27 | 1900-01-05 | 2017-07-28
Copy approval & POC feedback due | 2 | 1900-01-05 | 2017-07-28 | 1900-01-02 | 2017-08-01
Final copy to proofreading | 1 | 1900-01-02 | 2017-08-01 | 1900-01-03 | 2017-08-02
Design D1 to client | 4 | 1900-01-03 | 2017-08-02 | 1900-01-02 | 2017-08-08
Design D1 feedback due | 2 | 1900-01-02 | 2017-08-08 | 1900-01-04 | 2017-08-10
Design D2 to client | 1 | 1900-01-04 | 2017-08-10 | 1900-01-05 | 2017-08-11
Design approval due | 1 | 1900-01-05 | 2017-08-11 | 1900-01-01 | 2017-08-14
Proofreading | 1 | 1900-01-01 | 2017-08-14 | 1900-01-02 | 2017-08-15
Final e-book delivered to client | 1 | 1900-01-02 | 2017-08-15 | 1900-01-03 | 2017-08-16

## WHITE PAPER
PROJECT TIMELINE
WHITE PAPER | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Copy D1 to Design | 5 | 1900-01-04 | 2017-07-06 | 1900-01-04 | 2017-07-13
Copy D1 to client | 1 | 1900-01-04 | 2017-07-13 | 1900-01-05 | 2017-07-14
Copy D1 feedback due | 3 | 1900-01-05 | 2017-07-14 | 1900-01-03 | 2017-07-19
Copy D2 to client | 2 | 1900-01-03 | 2017-07-19 | 1900-01-05 | 2017-07-21
Copy D2 feedback due | 2 | 1900-01-05 | 2017-07-21 | 1900-01-02 | 2017-07-25
Copy D3 & POC to client | 1 | 1900-01-02 | 2017-07-25 | 1900-01-03 | 2017-07-26
Copy approval & POC feedback due | 2 | 1900-01-03 | 2017-07-26 | 1900-01-05 | 2017-07-28
Final copy to proofreading | 1 | 1900-01-05 | 2017-07-28 | 1900-01-01 | 2017-07-31
Design D1 to client | 3 | 1900-01-01 | 2017-07-31 | 1900-01-04 | 2017-08-03
Design D1 feedback due | 2 | 1900-01-04 | 2017-08-03 | 1900-01-01 | 2017-08-07
Design D2 to client | 2 | 1900-01-01 | 2017-08-07 | 1900-01-03 | 2017-08-09
Design D2 approval due | 1 | 1900-01-03 | 2017-08-09 | 1900-01-04 | 2017-08-10
Proofreading | 1 | 1900-01-04 | 2017-08-10 | 1900-01-05 | 2017-08-11
Final white paper delivered | 1 | 1900-01-05 | 2017-08-11 | 1900-01-01 | 2017-08-14
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)

## GBOOK
PROJECT TIMELINE
GBOOK | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Copy D1 to Design | 5 | 1900-01-04 | 2017-07-06 | 1900-01-04 | 2017-07-13
Copy D1 to client | 1 | 1900-01-04 | 2017-07-13 | 1900-01-05 | 2017-07-14
Copy D1 feedback due | 3 | 1900-01-05 | 2017-07-14 | 1900-01-03 | 2017-07-19
Copy D2 to client | 2 | 1900-01-03 | 2017-07-19 | 1900-01-05 | 2017-07-21
Copy D2 feedback due | 2 | 1900-01-05 | 2017-07-21 | 1900-01-02 | 2017-07-25
Copy D3 & POC to client | 1 | 1900-01-02 | 2017-07-25 | 1900-01-03 | 2017-07-26
Copy approval & POC feedback due | 2 | 1900-01-03 | 2017-07-26 | 1900-01-05 | 2017-07-28
Final copy to proofreading | 1 | 1900-01-05 | 2017-07-28 | 1900-01-01 | 2017-07-31
Layout L1 to client | 5 | 1900-01-01 | 2017-07-31 | 1900-01-01 | 2017-08-07
Layout L1 feedback due | 2 | 1900-01-01 | 2017-08-07 | 1900-01-03 | 2017-08-09
Layout L2 to client | 2 | 1900-01-03 | 2017-08-09 | 1900-01-05 | 2017-08-11
Layout L2 approval due | 2 | 1900-01-05 | 2017-08-11 | 1900-01-02 | 2017-08-15
Final layout to client for approval | 1 | 1900-01-02 | 2017-08-15 | 1900-01-03 | 2017-08-16
Final layout approval due | 1 | 1900-01-03 | 2017-08-16 | 1900-01-04 | 2017-08-17
Proofreading | 1 | 1900-01-04 | 2017-08-17 | 1900-01-05 | 2017-08-18
Final gbook delivered | 1 | 1900-01-05 | 2017-08-18 | 1900-01-01 | 2017-08-21
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Complete Date = WORKDAY([Task Start Date],[Days],Holidays!$A2:A11)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)
Task Start Date = [Task Complete Date, row above]

## INFOGRAPHIC
PROJECT TIMELINE
INFOGRAPHIC | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Copy D1 in wireframe to design and CS | 6 | 1900-01-04 | 2017-07-06 | 1900-01-05 | 2017-07-14
Copy D1 in wireframe to client | 1 | 1900-01-05 | 2017-07-14 | 1900-01-01 | 2017-07-17
Copy D1 feedback due | 3 | 1900-01-01 | 2017-07-17 | 1900-01-04 | 2017-07-20
Copy D2 to client | 2 | 1900-01-04 | 2017-07-20 | 1900-01-01 | 2017-07-24
Copy D2 feedback due | 2 | 1900-01-01 | 2017-07-24 | 1900-01-03 | 2017-07-26
Copy D3 & POC to client | 2 | 1900-01-03 | 2017-07-26 | 1900-01-05 | 2017-07-28
Copy approval & POC feedback due | 1 | 1900-01-05 | 2017-07-28 | 1900-01-01 | 2017-07-31
Final copy to proofreading | 1 | 1900-01-01 | 2017-07-31 | 1900-01-02 | 2017-08-01
Layout L1 to client | 6 | 1900-01-02 | 2017-08-01 | 1900-01-03 | 2017-08-09
Layout L1 feedback due | 2 | 1900-01-03 | 2017-08-09 | 1900-01-05 | 2017-08-11
Layout L2 to client | 2 | 1900-01-05 | 2017-08-11 | 1900-01-02 | 2017-08-15
Layout L2 approval due | 1 | 1900-01-02 | 2017-08-15 | 1900-01-03 | 2017-08-16
Final layout to client | 1 | 1900-01-03 | 2017-08-16 | 1900-01-04 | 2017-08-17
Final layout approval due | 1 | 1900-01-04 | 2017-08-17 | 1900-01-05 | 2017-08-18
Proofreading | 1 | 1900-01-05 | 2017-08-18 | 1900-01-01 | 2017-08-21
Final IG delivered | 1 | 1900-01-01 | 2017-08-21 | 1900-01-02 | 2017-08-22
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Complete Date = WORKDAY([Task Start Date],[Days],Holidays!$A2:A11)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)
Task Start Date = [Task Complete Date, row above]

## CEROS
PROJECT TIMELINE
CEROS | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Outline to Design for review | 5 | 1900-01-04 | 2017-07-06 | 1900-01-04 | 2017-07-13
Outline to client | 1 | 1900-01-04 | 2017-07-13 | 1900-01-05 | 2017-07-14
Outline feedback due | 2 | 1900-01-05 | 2017-07-14 | 1900-01-02 | 2017-07-18
Copy D1 to Design | 4 | 1900-01-02 | 2017-07-18 | 1900-01-01 | 2017-07-24
Copy D1 to client | 1 | 1900-01-01 | 2017-07-24 | 1900-01-02 | 2017-07-25
Copy D1 feedback due | 2 | 1900-01-02 | 2017-07-25 | 1900-01-04 | 2017-07-27
Copy D2 to client | 2 | 1900-01-04 | 2017-07-27 | 1900-01-01 | 2017-07-31
Copy D2 feedback due | 2 | 1900-01-01 | 2017-07-31 | 1900-01-03 | 2017-08-02
Copy D3 & POC to client | 1 | 1900-01-03 | 2017-08-02 | 1900-01-04 | 2017-08-03
Copy approval & POC feedback due | 2 | 1900-01-04 | 2017-08-03 | 1900-01-01 | 2017-08-07
Final copy to proofreading | 1 | 1900-01-01 | 2017-08-07 | 1900-01-02 | 2017-08-08
Design D1 to client | 4 | 1900-01-02 | 2017-08-08 | 1900-01-01 | 2017-08-14
Design D1 feedback due | 2 | 1900-01-01 | 2017-08-14 | 1900-01-03 | 2017-08-16
Design D2 to client | 2 | 1900-01-03 | 2017-08-16 | 1900-01-05 | 2017-08-18
Design D2 feedback due | 1 | 1900-01-05 | 2017-08-18 | 1900-01-01 | 2017-08-21
Coded Ceros to client | 6 | 1900-01-01 | 2017-08-21 | 1900-01-02 | 2017-08-29
Coded Ceros feedback due | 2 | 1900-01-02 | 2017-08-29 | 1900-01-04 | 2017-08-31
Ceros D2 to client | 2 | 1900-01-04 | 2017-08-31 | 1900-01-01 | 2017-09-04
Ceros D2 approval due | 1 | 1900-01-01 | 2017-09-04 | 1900-01-02 | 2017-09-05
Final Ceros delivered to client | 1 | 1900-01-02 | 2017-09-05 | 1900-01-03 | 2017-09-06
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)

## INTERACTIVE IG
PROJECT TIMELINE
INTERACTIVE INFOGRAPHIC | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Outline to Digital for review | 5 | 1900-01-04 | 2017-07-06 | 1900-01-04 | 2017-07-13
Outline to client | 1 | 1900-01-04 | 2017-07-13 | 1900-01-05 | 2017-07-14
Outline feedback due | 2 | 1900-01-05 | 2017-07-14 | 1900-01-02 | 2017-07-18
Copy D1 to Design | 4 | 1900-01-02 | 2017-07-18 | 1900-01-01 | 2017-07-24
Copy D1 to client | 1 | 1900-01-01 | 2017-07-24 | 1900-01-02 | 2017-07-25
Copy D1 feedback due | 2 | 1900-01-02 | 2017-07-25 | 1900-01-04 | 2017-07-27
Copy D2 to client | 2 | 1900-01-04 | 2017-07-27 | 1900-01-01 | 2017-07-31
Copy D2 feedback due | 2 | 1900-01-01 | 2017-07-31 | 1900-01-03 | 2017-08-02
Copy D3 & POC to client | 1 | 1900-01-03 | 2017-08-02 | 1900-01-04 | 2017-08-03
Copy approval & POC feedback due | 2 | 1900-01-04 | 2017-08-03 | 1900-01-01 | 2017-08-07
Final copy to proofreading | 1 | 1900-01-01 | 2017-08-07 | 1900-01-02 | 2017-08-08
Design D1 to client | 4 | 1900-01-02 | 2017-08-08 | 1900-01-01 | 2017-08-14
Design D1 feedback due | 2 | 1900-01-01 | 2017-08-14 | 1900-01-03 | 2017-08-16
Design D2 to client | 2 | 1900-01-03 | 2017-08-16 | 1900-01-05 | 2017-08-18
Design D2 approval due | 1 | 1900-01-05 | 2017-08-18 | 1900-01-01 | 2017-08-21
Coded IG to client | 6 | 1900-01-01 | 2017-08-21 | 1900-01-02 | 2017-08-29
Coded IG feedback due | 2 | 1900-01-02 | 2017-08-29 | 1900-01-04 | 2017-08-31
Coded IG D2 to client | 2 | 1900-01-04 | 2017-08-31 | 1900-01-01 | 2017-09-04
Coded IG D2 approval due | 1 | 1900-01-01 | 2017-09-04 | 1900-01-02 | 2017-09-05
Final coded IIG delivered to client | 1 | 1900-01-02 | 2017-09-05 | 1900-01-03 | 2017-09-06
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)

## LISTICLE
PROJECT TIMELINE
LISTICLE | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Wireframe to client | 3 | 1900-01-04 | 2017-07-06 | 1900-01-02 | 2017-07-11
Wireframe feedback due | 2 | 1900-01-02 | 2017-07-11 | 1900-01-04 | 2017-07-13
Copy D1 to digital for review | 4 | 1900-01-04 | 2017-07-13 | 1900-01-03 | 2017-07-19
Copy D1 to client | 1 | 1900-01-03 | 2017-07-19 | 1900-01-04 | 2017-07-20
Copy D1 feedback due | 2 | 1900-01-04 | 2017-07-20 | 1900-01-01 | 2017-07-24
Copy D2 to client | 3 | 1900-01-01 | 2017-07-24 | 1900-01-04 | 2017-07-27
Copy D2 feedback due | 2 | 1900-01-04 | 2017-07-27 | 1900-01-01 | 2017-07-31
Final copy to client & proofing; prelim design/POC to client | 2 | 1900-01-01 | 2017-07-31 | 1900-01-03 | 2017-08-02
Prelim design/POC feedback due | 2 | 1900-01-03 | 2017-08-02 | 1900-01-05 | 2017-08-04
Full layout L1 to client | 2 | 1900-01-05 | 2017-08-04 | 1900-01-02 | 2017-08-08
Full layout L1 feedback due | 2 | 1900-01-02 | 2017-08-08 | 1900-01-04 | 2017-08-10
Full layout L2 to client | 2 | 1900-01-04 | 2017-08-10 | 1900-01-01 | 2017-08-14
Full layout L2 feedback due | 2 | 1900-01-01 | 2017-08-14 | 1900-01-03 | 2017-08-16
Functional proof to C4D | 5 | 1900-01-03 | 2017-08-16 | 1900-01-03 | 2017-08-23
Internal edits to coder | 2 | 1900-01-03 | 2017-08-23 | 1900-01-05 | 2017-08-25
Functional proof to client | 2 | 1900-01-05 | 2017-08-25 | 1900-01-02 | 2017-08-29
Functional proof feedback due | 2 | 1900-01-02 | 2017-08-29 | 1900-01-04 | 2017-08-31
Final proofreading | 1 | 1900-01-04 | 2017-08-31 | 1900-01-05 | 2017-09-01
Final listicle & files delivered to client | 1 | 1900-01-05 | 2017-09-01 | 1900-01-02 | 2017-09-05
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Complete Date = WORKDAY([Task Start Date],[Days],Holidays!$A2:A11)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)

## iPAPER
PROJECT TIMELINE
iPAPER | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Wireframe to client | 3 | 1900-01-04 | 2017-07-06 | 1900-01-02 | 2017-07-11
Wireframe feedback due | 2 | 1900-01-02 | 2017-07-11 | 1900-01-04 | 2017-07-13
Copy D1 to digital and CS for review | 5 | 1900-01-04 | 2017-07-13 | 1900-01-04 | 2017-07-20
Copy D1 to client | 1 | 1900-01-04 | 2017-07-20 | 1900-01-05 | 2017-07-21
Copy D1 feedback due | 3 | 1900-01-05 | 2017-07-21 | 1900-01-03 | 2017-07-26
Copy D2 to client | 3 | 1900-01-03 | 2017-07-26 | 1900-01-01 | 2017-07-31
Copy D2 feedback due | 2 | 1900-01-01 | 2017-07-31 | 1900-01-03 | 2017-08-02
Final copy to client & proofing; prelim design/POC L1 to client | 2 | 1900-01-03 | 2017-08-02 | 1900-01-05 | 2017-08-04
Copy approval due; prelim design/POC L1 feedback due | 2 | 1900-01-05 | 2017-08-04 | 1900-01-02 | 2017-08-08
Full layout L1 to client | 2 | 1900-01-02 | 2017-08-08 | 1900-01-04 | 2017-08-10
Full layout L1 feedback due | 2 | 1900-01-04 | 2017-08-10 | 1900-01-01 | 2017-08-14
Full layout L2 to client | 2 | 1900-01-01 | 2017-08-14 | 1900-01-03 | 2017-08-16
Full layout L2 feedback due | 2 | 1900-01-03 | 2017-08-16 | 1900-01-05 | 2017-08-18
Functional proof to C4D | 7 | 1900-01-05 | 2017-08-18 | 1900-01-02 | 2017-08-29
Internal edits to coder | 2 | 1900-01-02 | 2017-08-29 | 1900-01-04 | 2017-08-31
Functional proof to client | 2 | 1900-01-04 | 2017-08-31 | 1900-01-01 | 2017-09-04
Functional proof feedback due | 2 | 1900-01-01 | 2017-09-04 | 1900-01-03 | 2017-09-06
Final proof to client | 1 | 1900-01-03 | 2017-09-06 | 1900-01-04 | 2017-09-07
Receive approval, proof, and delivered final files to client | 1 | 1900-01-04 | 2017-09-07 | 1900-01-05 | 2017-09-08
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)

## QUIZ
PROJECT TIMELINE
QUIZ | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Copy D1 to digital and CS for review | 5 | 1900-01-04 | 2017-07-06 | 1900-01-04 | 2017-07-13
Copy D1 to client | 1 | 1900-01-04 | 2017-07-13 | 1900-01-05 | 2017-07-14
Copy D1 feedback due | 2 | 1900-01-05 | 2017-07-14 | 1900-01-02 | 2017-07-18
Copy D2 to client | 3 | 1900-01-02 | 2017-07-18 | 1900-01-05 | 2017-07-21
Copy D2 feedback due | 2 | 1900-01-05 | 2017-07-21 | 1900-01-02 | 2017-07-25
Final copy and POC to client | 2 | 1900-01-02 | 2017-07-25 | 1900-01-04 | 2017-07-27
Copy approval due. Feedback on POC due. | 2 | 1900-01-04 | 2017-07-27 | 1900-01-01 | 2017-07-31
Full design L1 to client | 3 | 1900-01-01 | 2017-07-31 | 1900-01-04 | 2017-08-03
Full design L1 feedback due | 2 | 1900-01-04 | 2017-08-03 | 1900-01-01 | 2017-08-07
Full design L2 to client | 2 | 1900-01-01 | 2017-08-07 | 1900-01-03 | 2017-08-09
Full design L2 feedback L2 | 2 | 1900-01-03 | 2017-08-09 | 1900-01-05 | 2017-08-11
Functional proof to C4D | 5 | 1900-01-05 | 2017-08-11 | 1900-01-05 | 2017-08-18
Internal edits to coder | 3 | 1900-01-05 | 2017-08-18 | 1900-01-03 | 2017-08-23
Functional proof to client | 2 | 1900-01-03 | 2017-08-23 | 1900-01-05 | 2017-08-25
Functional proof feedback due | 2 | 1900-01-05 | 2017-08-25 | 1900-01-02 | 2017-08-29
Final proof to client & approval due | 2 | 1900-01-02 | 2017-08-29 | 1900-01-04 | 2017-08-31
Final proofreading | 1 | 1900-01-04 | 2017-08-31 | 1900-01-05 | 2017-09-01
Finalization call with client | 1 | 1900-01-05 | 2017-09-01 | 1900-01-01 | 2017-09-04
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)

## ASSESSMENT
PROJECT TIMELINE
ASSESSMENT | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Wireframe to client | 3 | 1900-01-04 | 2017-07-06 | 1900-01-02 | 2017-07-11
Wireframe feedback due | 2 | 1900-01-02 | 2017-07-11 | 1900-01-04 | 2017-07-13
Copy D1 to digital for review | 5 | 1900-01-04 | 2017-07-13 | 1900-01-04 | 2017-07-20
Copy D1 to client | 1 | 1900-01-04 | 2017-07-20 | 1900-01-05 | 2017-07-21
Copy D1 feedback due | 2 | 1900-01-05 | 2017-07-21 | 1900-01-02 | 2017-07-25
Copy D2 to client | 3 | 1900-01-02 | 2017-07-25 | 1900-01-05 | 2017-07-28
Copy D2 feedback due | 2 | 1900-01-05 | 2017-07-28 | 1900-01-02 | 2017-08-01
Final copy to client. POC to client. | 2 | 1900-01-02 | 2017-08-01 | 1900-01-04 | 2017-08-03
Final copy approval due. POC feedback due. | 2 | 1900-01-04 | 2017-08-03 | 1900-01-01 | 2017-08-07
Full layout L1 to client | 3 | 1900-01-01 | 2017-08-07 | 1900-01-04 | 2017-08-10
Full layout L1 feedback due | 2 | 1900-01-04 | 2017-08-10 | 1900-01-01 | 2017-08-14
Full layout L2 to client | 2 | 1900-01-01 | 2017-08-14 | 1900-01-03 | 2017-08-16
Full layout L2 feedback due | 2 | 1900-01-03 | 2017-08-16 | 1900-01-05 | 2017-08-18
Functional proof to C4D | 7 | 1900-01-05 | 2017-08-18 | 1900-01-02 | 2017-08-29
Internal edits to coder | 2 | 1900-01-02 | 2017-08-29 | 1900-01-04 | 2017-08-31
Functional proof to client | 2 | 1900-01-04 | 2017-08-31 | 1900-01-02 | 2017-09-05
Functional proof feedback due | 2 | 1900-01-01 | 2017-09-04 | 1900-01-03 | 2017-09-06
Final proof to client | 1 | 1900-01-03 | 2017-09-06 | 1900-01-04 | 2017-09-07
Final approval due | 1 | 1900-01-04 | 2017-09-07 | 1900-01-05 | 2017-09-08
Final proofreading | 1 | 1900-01-05 | 2017-09-08 | 1900-01-01 | 2017-09-11
Finalization call with client | 1 | 1900-01-01 | 2017-09-11 | 1900-01-02 | 2017-09-12
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Complete Date = WORKDAY([Task Start Date],[Days],Holidays!$A2:A11)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)
Task Start Date = [Task Complete Date, row above]

## MVID-MM
PROJECT TIMELINE
MVID-MM | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Present storyline to client for feedback | 6 | 1900-01-04 | 2017-07-06 | 1900-01-05 | 2017-07-14
Script D1 presentation | 10 | 1900-01-05 | 2017-07-14 | 1900-01-05 | 2017-07-28
Script D1 feedback due | 3 | 1900-01-05 | 2017-07-28 | 1900-01-03 | 2017-08-02
Script D2 complete | 2 | 1900-01-03 | 2017-08-02 | 1900-01-05 | 2017-08-04
Storyboard D1 complete | 3 | 1900-01-05 | 2017-08-04 | 1900-01-03 | 2017-08-09
Storyboard D1 presentation | 1 | 1900-01-03 | 2017-08-09 | 1900-01-04 | 2017-08-10
Storyboard D1 feedback due | 3 | 1900-01-04 | 2017-08-10 | 1900-01-02 | 2017-08-15
Final storyboard, VO & music options to client | 3 | 1900-01-02 | 2017-08-15 | 1900-01-05 | 2017-08-18
Final storyboard, VO & music feedback due | 3 | 1900-01-05 | 2017-08-18 | 1900-01-03 | 2017-08-23
VO demo sent to client | 1 | 1900-01-03 | 2017-08-23 | 1900-01-04 | 2017-08-24
VO demo approval due | 1 | 1900-01-04 | 2017-08-24 | 1900-01-05 | 2017-08-25
VO recording sent to design | 1 | 1900-01-05 | 2017-08-25 | 1900-01-01 | 2017-08-28
Animation sent to client | 4 | 1900-01-01 | 2017-08-28 | 1900-01-05 | 2017-09-01
Animation feedback due | 2 | 1900-01-05 | 2017-09-01 | 1900-01-03 | 2017-09-06
Final video sent to client | 2 | 1900-01-02 | 2017-09-05 | 1900-01-04 | 2017-09-07
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Complete Date = WORKDAY([Task Start Date],[Days],Holidays!$A2:A11)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)

## MVID-S & MVID-KT
PROJECT TIMELINE
MVID-S/MVID-KT | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Present storyline to client for feedback | 6 | 1900-01-04 | 2017-07-06 | 1900-01-05 | 2017-07-14
Script D1 presentation | 10 | 1900-01-05 | 2017-07-14 | 1900-01-05 | 2017-07-28
Script D1 feedback due | 3 | 1900-01-05 | 2017-07-28 | 1900-01-03 | 2017-08-02
Script D2 complete | 2 | 1900-01-03 | 2017-08-02 | 1900-01-05 | 2017-08-04
Storyboard D1 complete | 7 | 1900-01-05 | 2017-08-04 | 1900-01-02 | 2017-08-15
Storyboard D1 presentation | 1 | 1900-01-02 | 2017-08-15 | 1900-01-03 | 2017-08-16
Storyboard D1 feedback due | 3 | 1900-01-03 | 2017-08-16 | 1900-01-01 | 2017-08-21
Final storyboard, VO & music options to client | 3 | 1900-01-01 | 2017-08-21 | 1900-01-04 | 2017-08-24
Final storyboard, VO & music feedback due | 3 | 1900-01-04 | 2017-08-24 | 1900-01-02 | 2017-08-29
VO demo sent to client | 1 | 1900-01-02 | 2017-08-29 | 1900-01-03 | 2017-08-30
VO demo approval due | 1 | 1900-01-03 | 2017-08-30 | 1900-01-04 | 2017-08-31
VO recording sent to design | 1 | 1900-01-04 | 2017-08-31 | 1900-01-05 | 2017-09-01
Animation sent to client | 6 | 1900-01-05 | 2017-09-01 | 1900-01-02 | 2017-09-12
Animation feedback due | 2 | 1900-01-01 | 2017-09-11 | 1900-01-03 | 2017-09-13
Final video sent to client | 2 | 1900-01-03 | 2017-09-13 | 1900-01-05 | 2017-09-15
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Complete Date = WORKDAY([Task Start Date],[Days],Holidays!$A2:A11)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)

## MVID-A
PROJECT TIMELINE
MVID-A | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Present storyline to client for feedback | 6 | 1900-01-04 | 2017-07-06 | 1900-01-05 | 2017-07-14
Script D1 presentation | 10 | 1900-01-05 | 2017-07-14 | 1900-01-05 | 2017-07-28
Script D1 feedback due | 3 | 1900-01-05 | 2017-07-28 | 1900-01-03 | 2017-08-02
Script D2 complete | 2 | 1900-01-03 | 2017-08-02 | 1900-01-05 | 2017-08-04
Storyboard D1 complete | 10 | 1900-01-05 | 2017-08-04 | 1900-01-05 | 2017-08-18
Storyboard D1 presentation | 1 | 1900-01-05 | 2017-08-18 | 1900-01-01 | 2017-08-21
Storyboard D1 feedback due | 3 | 1900-01-01 | 2017-08-21 | 1900-01-04 | 2017-08-24
Final storyboard, VO & music options to client | 3 | 1900-01-04 | 2017-08-24 | 1900-01-02 | 2017-08-29
Final storyboard, VO & music feedback due | 3 | 1900-01-02 | 2017-08-29 | 1900-01-05 | 2017-09-01
VO demo sent to client | 1 | 1900-01-05 | 2017-09-01 | 1900-01-02 | 2017-09-05
VO demo approval due | 1 | 1900-01-01 | 2017-09-04 | 1900-01-02 | 2017-09-05
VO recording sent to design | 1 | 1900-01-02 | 2017-09-05 | 1900-01-03 | 2017-09-06
Animation sent to client | 8 | 1900-01-03 | 2017-09-06 | 1900-01-01 | 2017-09-18
Animation feedback due | 2 | 1900-01-01 | 2017-09-18 | 1900-01-03 | 2017-09-20
Final video sent to client | 2 | 1900-01-03 | 2017-09-20 | 1900-01-05 | 2017-09-22
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Complete Date = WORKDAY([Task Start Date],[Days],Holidays!$A2:A11)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)

## BLOG
PROJECT TIMELINE
BLOG POST | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Copy D1 to Client | 4 | 1900-01-04 | 2017-07-06 | 1900-01-03 | 2017-07-12
Copy D1 feedback due | 2 | 1900-01-03 | 2017-07-12 | 1900-01-05 | 2017-07-14
Copy D2 to client | 2 | 1900-01-05 | 2017-07-14 | 1900-01-02 | 2017-07-18
Copy D2 feedback/approval due | 2 | 1900-01-02 | 2017-07-18 | 1900-01-04 | 2017-07-20
Final copy to client | 1 | 1900-01-04 | 2017-07-20 | 1900-01-05 | 2017-07-21
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Complete Date = WORKDAY([Task Start Date],[Days],Holidays!$A2:A11)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)

## FACT SHEET
PROJECT TIMELINE
FACT SHEET | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Copy D1 to Design | 5 | 1900-01-04 | 2017-07-06 | 1900-01-04 | 2017-07-13
Copy D1 to client | 1 | 1900-01-04 | 2017-07-13 | 1900-01-05 | 2017-07-14
Copy D1 feedback due | 2 | 1900-01-05 | 2017-07-14 | 1900-01-02 | 2017-07-18
Copy D2 to client | 2 | 1900-01-02 | 2017-07-18 | 1900-01-04 | 2017-07-20
Copy D2 feedback due | 2 | 1900-01-04 | 2017-07-20 | 1900-01-01 | 2017-07-24
Copy D3 & POC to client | 1 | 1900-01-01 | 2017-07-24 | 1900-01-02 | 2017-07-25
Copy approval & POC feedback due | 2 | 1900-01-02 | 2017-07-25 | 1900-01-04 | 2017-07-27
Final copy to proofreading | 1 | 1900-01-04 | 2017-07-27 | 1900-01-05 | 2017-07-28
Design D1 to client | 1 | 1900-01-05 | 2017-07-28 | 1900-01-01 | 2017-07-31
Design D1 feedback due | 1 | 1900-01-01 | 2017-07-31 | 1900-01-02 | 2017-08-01
Design D2 to client | 1 | 1900-01-02 | 2017-08-01 | 1900-01-03 | 2017-08-02
Design D2 feedback due | 1 | 1900-01-03 | 2017-08-02 | 1900-01-04 | 2017-08-03
Final layout to client | 1 | 1900-01-04 | 2017-08-03 | 1900-01-05 | 2017-08-04
Final approval due | 1 | 1900-01-05 | 2017-08-04 | 1900-01-01 | 2017-08-07
Proofreading | 1 | 1900-01-01 | 2017-08-07 | 1900-01-02 | 2017-08-08
Final files delivered | 1 | 1900-01-02 | 2017-08-08 | 1900-01-03 | 2017-08-09
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Complete Date = WORKDAY([Task Start Date],[Days],Holidays!$A2:A11)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)

## Q&A
PROJECT TIMELINE
Q&A | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Copy D1 to Design | 5 | 1900-01-04 | 2017-07-06 | 1900-01-04 | 2017-07-13
Copy D1 to client | 1 | 1900-01-04 | 2017-07-13 | 1900-01-05 | 2017-07-14
Copy D1 feedback due | 2 | 1900-01-05 | 2017-07-14 | 1900-01-02 | 2017-07-18
Copy D2 to client | 2 | 1900-01-02 | 2017-07-18 | 1900-01-04 | 2017-07-20
Copy D2 feedback due | 2 | 1900-01-04 | 2017-07-20 | 1900-01-01 | 2017-07-24
Copy D3 & POC to client | 2 | 1900-01-01 | 2017-07-24 | 1900-01-03 | 2017-07-26
Copy approval & POC feedback due | 2 | 1900-01-03 | 2017-07-26 | 1900-01-05 | 2017-07-28
Final copy to proofreading | 1 | 1900-01-05 | 2017-07-28 | 1900-01-01 | 2017-07-31
Design D1 to client | 3 | 1900-01-01 | 2017-07-31 | 1900-01-04 | 2017-08-03
Design D1 feedback due | 2 | 1900-01-04 | 2017-08-03 | 1900-01-01 | 2017-08-07
Design D2 to client | 1 | 1900-01-01 | 2017-08-07 | 1900-01-02 | 2017-08-08
Design D2 feedback due | 1 | 1900-01-02 | 2017-08-08 | 1900-01-03 | 2017-08-09
Proofreading | 1 | 1900-01-03 | 2017-08-09 | 1900-01-04 | 2017-08-10
Final files delivered | 1 | 1900-01-04 | 2017-08-10 | 1900-01-05 | 2017-08-11
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Complete Date = WORKDAY([Task Start Date],[Days],Holidays!$A2:A11)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)
Task Start Date = [Task Complete Date, row above]

## BLANK
PROJECT TIMELINE
GENERIC | CLIENT NAME - ASSET ID# - ASSET TITLE
Task Description of the tasks required to complete the project | Days # of days required to complete task | Task Start Date Date the task is scheduled to begin |  | Task Complete Date Date the task is scheduled to be complete
Task | Days | Task Start | Task Start Date | Task Complete | Task Complete Date
SME call | 1 | 1900-01-03 | 2017-07-05 | 1900-01-04 | 2017-07-06
Outline to Client | 3 | 1900-01-04 | 2017-07-06 | 1900-01-02 | 2017-07-11
Outline feedback due | 1 | 1900-01-02 | 2017-07-11 | 1900-01-03 | 2017-07-12
Copy D1 to Design | 5 | 1900-01-03 | 2017-07-12 | 1900-01-03 | 2017-07-19
Copy D1 to client | 1 | 1900-01-03 | 2017-07-19 | 1900-01-04 | 2017-07-20
Copy D1 feedback due | 2 | 1900-01-04 | 2017-07-20 | 1900-01-01 | 2017-07-24
Copy D2 to client | 2 | 1900-01-01 | 2017-07-24 | 1900-01-03 | 2017-07-26
Copy D2 feedback due | 2 | 1900-01-03 | 2017-07-26 | 1900-01-05 | 2017-07-28
Copy D3 & POC to client | 2 | 1900-01-05 | 2017-07-28 | 1900-01-02 | 2017-08-01
Copy approval & POC feedback due | 2 | 1900-01-02 | 2017-08-01 | 1900-01-04 | 2017-08-03
Final copy to proofreading | 1 | 1900-01-04 | 2017-08-03 | 1900-01-05 | 2017-08-04
Design D1 to client | 3 | 1900-01-05 | 2017-08-04 | 1900-01-03 | 2017-08-09
Design D1 feedback due | 2 | 1900-01-03 | 2017-08-09 | 1900-01-05 | 2017-08-11
Design D2 to client | 1 | 1900-01-05 | 2017-08-11 | 1900-01-01 | 2017-08-14
Design approval due | 1 | 1900-01-01 | 2017-08-14 | 1900-01-02 | 2017-08-15
Proofreading | 1 | 1900-01-02 | 2017-08-15 | 1900-01-03 | 2017-08-16
Final files delivered | 1 | 1900-01-03 | 2017-08-16 | 1900-01-04 | 2017-08-17
Formulas:
Task Start = WEEKDAY([Task Start Date])
Task Complete = WEEKDAY([Task Complete Date])
Task Complete Date = WORKDAY([Task Start Date],[Days],J5)
Task Complete Date = WORKDAY([Task Start Date],[Days],Holidays!$A2:A11)
Task Start Date = WORKDAY([Task Start Date, row above],[Days, row above],J5)
Task Start Date = [Task Complete Date, row above]

## Holidays (hidden)
Holidays
2017-01-02
2017-01-16
2017-02-20
2017-05-29
2017-07-04
2017-09-04
2017-11-10
2017-11-23
2017-11-24
2017-12-25
H